## Sheet1
|  |  |  | (A) | Approved | (C)
|  |  |  | Original | Change Orders | Adjusted
Type of Work |  | Contractor (see attached |  | Contract | and/or | Contract
|  | list for addresses) | Phone | Amount | Credits | Amount (A+B) |  |  |  | Cellia
- |  | ------------------------ |  | ----------- | ----------- | -----------
Underground |  | Mancini Sewer & Water |  | 47348 | 3055 | 50403
Excavating |  | Spinolas Brothers | ? | 115000 | 10208.32 | 125208.32 |  |  |  | Apron south | 368
Concrete |  | Mohawk Contracting Co. |  | 175100 | 17518.55 | 192618.55 |  |  |  | north | 516.8625
Steel |  | Vaughn Industrial Sales |  | 227000 | 16214 | 243214 |  |  |  |  | 884.8625 | 3539.45
Curbs |  | Cella Concrete, Inc. |  | 18875 | 9077.81 | 27952.81
Paving |  | Northern Paving, Inc. |  | 53833 | 10063.25 | 63896.25 |  |  |  | Walks | 65.975
Pre-Cast Slabs |  | Midwest Flexicore |  | 42942 | 2750 | 45692 |  |  |  |  | 45.44
Roof |  | Regal Roofing Co. | 847-299-1110 | 38375 | 2630 | 41005 |  |  |  |  | 1160.3412
Plumbing |  | P & P Plumbing & Heating |  | 121000 | 3756 | 124756 |  |  |  |  | 307.2937
Masonry |  | Hendersons' Construction |  | 69500 | 9643.5 | 79143.5 |  |  |  | 91.6667 | 1579.0499 | 3473.9099
Exterior Plaster |  | R.G. Interiors, Inc. |  | 97035 | 1563 | 98598
Dampproof |  | Air Pressure Dampproofing |  | 6625 |  | 6625 | [5 empty] | 7013.3599 | 6989.8
Atrium |  | View Thru | 847-352-1232 | 25845 |  | 25845
Glass & Glazing |  | Capitol Glass |  | 75731 | 6747 | 82478
HVAC |  | Edwards Engineering |  | 500000 | 13762 | 513762
Electrical: | [11 empty] | 3341.8
Transformer |  | Riviera Transformer Co. |  | 1541.81 |  | 1541.81
Electric |  | Waco Electric Corporation |  | 267500 | 33759.08 | 301259.08 | [5 empty] | 3648
Fire Protection |  | Valley Automatic Sprinkler |  | 46900 | 4570 | 51470 | [5 empty] | 17279.1
Accoust Ceilings |  | Noonan |  | 47465 | 5800 | 53265 | [5 empty] | 200
Elevator |  | Dover Elevator Co. |  | 35175 | 125 | 35300 | [5 empty] | 2664.28
Drywall |  | R.G. Interiors Inc. |  | 94710 | 1829.45 | 96539.45 | [5 empty] | 27133.18
Wood Doors & Frm |  | Imperial Woodwork |  | 35098 |  | 35098 | [5 empty] | 13797
Metal Doors & Frm |  | M & F |  | 18700 |  | 18700 | [5 empty] | 13336.18
Hardware--Doors |  | Lind |  | 10450 |  | 10450
Lab Casework |  | St. Charles |  | 103914 |  | 103914
Carpeting |  | Northern Carpeting |  | 20351.93 |  | 20351.93
Floors, |  | Dimensional Flooring |  | 32497 | 3385.75 | 35882.75
Painting |  | Cambell |  | 32535.4 | 5806 | 38341.4
Cabinets & Countertops |  | St. Charles |  | 8091.43 |  | 8091.43
Reception Desks /Panel |  | Hire-Nelson |  | 23632 | 3203 | 26835
Landscaping |  | Green Rose |  | 30000 |  | 30000
Toilet Partitions |  | Knickerbocker |  | 4045 |  | 4045
CMC Ed Hanson
HVAC Controls |  | Landis & Gyr Powers |  | 130996 | -4464.6 | 126531.4
Security System |  | Norman Securities |  | 15965 | 1035 | 17000
Construction Mgmt |  | DPCM Group |  | 130000 |  | 130000
Permits |  | Palatine Village |  | 16205.83 |  | 16205.83
Electric-Exterior |  | Commonwealth Edison |  | 9267.95 |  | 9267.95
Water Chiller |  | Carrier Corporation |  | 51265.63 |  | 51265.63
Heat Boilers:
Boiler |  | Barr Mechanical Sales |  | 23005 |  | 23005
Humidif. Boiler |  | Steam Sales Corporation |  | 11725.36 |  | 11725.36
Water Treatment |  | Hi-Tech |  | 5000 |  | 5000
Cooling Tower |  | Bullack |  | 2800 |  | 2800
Air Handling |  | USA Coil & Air, Inc. |  | 32708 |  | 32708
Lab Exhaust Stack & fan |  | Palatine Welding + CAE+Himelblau |  | 6756.2 |  | 6756.2
Perchl. Exhaust |  | spray sys + Chi blow pipe+ Kawanee |  | 1105.28 |  | 1105.28
Blue Board |  | Expense |  | 1500 |  | 1500
Loading Dock Wall |  | Expense |  | 700 |  | 700
Generator |  | O'Brien Machinery |  | 7800 |  | 7800
Variable Speed Drives |  | John Willis Company |  | 14000 |  | 14000
Skylights |  | Aurburn Plastics |  | 1359.35 |  | 1359.35
Phone System |  | ADM & Centel |  | 6000 |  | 6000
Phone & network Install |  | Centel |  | 42000 |  | 42000
Computer Network |  | NOT LET |  |  |  | 0
Computer HVAC etc |  | Computerland |  | 3000 |  | 3000
Drywall Lower Level
Well |  |  |  | 2400 |  | 2400
Testing Plateform |  | Knoll | ? | 12000 |  | 12000
Gas Pipe Line |  | Columbia & R12 | ? | 1945.5 |  | 1945.5
Architect & Eng. |  | Blauck |  | 2000 |  | 2000
Contingency |  |  |  | 194341.25 |  | 162037.11
|  |  |  | ----------- | ----------- | -----------
Total Construction Escrow Cost |  |  |  | 3152661.92 | 162037.11 | 3282394.89
Original Mortgage |  |  |  | 347338.08 |  | 347338.08
|  |  |  | ----------- | ----------- | -----------
TOTAL CONSTRUCTION LOAN |  |  |  | 3500000 | 162037.11 | 3629732.97
architech |  | Ruben Anastacico
|  |  |  | (A) | (B) | (C)
|  |  |  | Original | Change Orders | Adjusted
Type of Work |  | Contractor |  | Contract | and/or | Contract
|  |  |  | Amount | Credits | Amount (A+B)
- |  | - |  | ----------- | ----------- | -----------
Village Fees |  | Palatine Village |  | 749.97 |  | 749.97
Road Extension |  | Palatine Village |  | 44878 |  | 44878
AEI Engineers |  |  |  | 19000 |  | 19000
Financing:
Construction Pt. |  |  |  | 31850 |  | 31850
Lending Pt.
Realtor Pt.
Other Fees |  |  |  | 15000 |  | 15000
Interest |  |  |  | 122700 |  | 122700
Legal & Acctg. |  |  |  | 15000 |  | 15000
Insurance & Taxes |  |  |  | 15000 |  | 15000
|  |  |  | ----------- | ----------- | -----------
Other Fees & Soft Costs |  |  |  | 264177.97 | 0 | 264177.97
Total Costs |  |  |  | 3764177.97 |  | 3893910.94
|  |  |  | Requested | CAE Approved | DCPM Approved | Not Allowed | Approved | Has been
|  | Mancini Sewer & Water |  | Extra or Credit |  |  |  | Backcharge | Invoiced
| 1 | 12" RCP 30 ft long @ basin 7 | * | 1085 | 1085
| 2 | 6"PVC pipe from parking lot to str | * | 1970 | 1970
| 3 | 36" Sump Basin |  | 787.5 | DPCM or NO |  | 787.5
| 4 | Washed stone in basement |  | 630 |  |  | 630
| 5 | Connect drain tile where? |  | 200 | May be CAE | 200
| 6 | Stone for undercutting to connect |  | 100 |  | 100
| 7 | Trench backfill in area of drain |  | 80 |  | 80
| 8 | Iron pipe for storm |  | 220 |  |  | 220
|  | Credit for tile installed by CAE |  | -628
Fix leaks around pipes thru wall
|  | TOTAL |  | 4444.5 | 3055 | 0 | 787.5 | 0 | 0
Spinolas Brothers
| 1 | 200 Hitachi for 8 hours | * | 800 | 800 | see Ed
| 2 | Extra days for overdig @$400/day | * | 1600 | 1600
|  | 3" limestone in place |  | 3430.14 | 3430.14
|  | Pea gravel between buildings |  | 5635.33
0 |  | Undercuts and 3" stone |  | 3862.44 |  | 3862.44
|  | Undercuts and 3" stone |  | 957.74 |  | 957.74
|  | Pea Gravel |  | 758.12
|  | Pea Gravel |  | 753.06
|  | 3" limestone |  | 956.02
|  | Extra excavation undercut parking |  | 4669
|  | Compaction-c.y. on site material |  | 1667.5
| 3 | Grade 9 - Delivered & placed | * | 308 | 308
| 4 | Credit for parking lot fill | * | -750 | -750
|  | TOTAL |  | 24647.35 | 5388.14 | 4820.18 | 0
Vaughn Industrial Sales
| 1 | Misc Field Extras Jan 16, 1991
|  | B3 Shortened |  | 1515
|  | Beams Shortened due to footings |  | 2400
|  | B20 & B21 Wall moved |  | 2880
|  | G5 & H4 Move & relocate |  | 1229
|  | Use Crane to lower Air Handlers |  | 600
|  | Add Grating support steel |  | 6616
| 2 | Cooling Tower Move |  | 1811
| 3 | Roof Frame |  | 613
|  | Remove 2 frames, cut BEAM, 3 frames |  | 770 | 0 | See Ed | 770
|  | Mason and Flexcore Repairs |  | -1220
|  | Credit for roof ladder |  | -1000
|  | TOTAL |  | 16214 | 0 | 0 | 0
Cella Concrete, Inc.
| 1 | Additional curb, gutter, drive apron | * | 5393.9 | 5393.9
| 2 | Removal of curb on Wood Street | * | 200 | 200
| 3 | 247.84 tons of CA-6 sub base | * | 2664.28 | 2664.28 |  |  | 0 | 0
| 4 | Replace 39.5 l.f. curb & gutter | * | 819.63 | 819.63
|  | TOTAL |  | 9077.81 | 9077.81 | 0 |  | 0
Northern Paving, Inc.
| 1 | Grade 9 gravel to #3 rock | * | 1560 | 1560
| 2 | Ground stabilization fabric | * | 1000 | 1000
| 3 | Raise Wood Street | * | 6642 | 6642
| 4 | Gravel for parking lot | * | 861.25 | 861.25 |  | 1722.5
|  | TOTAL |  | 10063.25 | 10063.25 | 0 | 1722.5
Midwest Flexicore
| 1 | Extra trip charge |  | 750 | 750
| 2 | Additional erection trip for slabs |  | 2000 | 2000
|  | TOTAL |  | 2750 | 2750 | 0 | 0
Regal Roofing Co.
| 1 | Extra granuales | * | 1600 | 1600
| 2 | Move scuttle & curbs, reflash | * | 1030 | 1030
|  | TOTAL |  | 2630 | 2630 | 0 | 0
P & P Plumbing & Heating
| 1 | 1-hr labor for elevator drain | * | 50 | 50
| 2 | Layout walls | * | 100 |  | 100
| 3 | Layout walls | * | 150 |  | 150
| 4 | raise hangers | * | 100 | 100 |  | 100
| 5 | Install sump in elevator pit | * | 289 | 289 |  |  | 0
| 6 | Repair leak in hot water | * | 51.5 | 51.5 |  | 51.5
| 7 | Install sink in president's office | * | 536 | 536
| 8 | Relocate plumbing in lunch room | * | 169 | 169
| 9 | Reroute 4" vent stack |  | 623
| 10 | Relocate cooling tower main |  | 404
| 11 | Credit for Change Order #6 | * | -51.5 | -51.5 |  | 151.5
| 12 | Change east downspout | * | 161 | 161
| 13 | Add boiler drain in janitor's closet | * | 81 | 81
| 14 | Lower vent bar and move water line |  | 254
| 15 | Sink and faucet for Roy's lab | * | 420 | 420
| 16 | Install backflow preventor | * | 900 | 900
| 17 | Line for hood wash down | * | 800 | 800
Vacuum breaker credit
|  | TOTAL |  | 5037 | 3506 | 250 |  | Mohawk
Waco Electric Corporation
| 1 | 120/240 V connection | * | 7437 | 7437
| 2 | Revised floor duct to flush type | * | 510 | 510
| 3 | Revised motor control center | * | -345 | -345
| 4 | Conduit under parking | * | 980 | 980
| 5 | Basement lighting | * | 6679 | 6679
| 6 | Cable tray system | * | -5848 | -5848
| 7 | UPS extra circuits | * | 5171 | 5171
| 8 | Install temp pole & trailer service | * | 968.42 | 968.42
| 22 | Install concrete pole bases | * | 1711.5 | 1711.5
| 14 | Extra phone conduit | * | 884 | 884
| 9 | 2 additional outlets in vending area | * | 186 | 186
| 10 | Dishwasher in vending area | * | 134 | 134
| 11 | 110 outlets in room 110 | * | 174 | 174
| 12 | Temp wiring to sump pumps and pit | * | 356.17 | 356.17
| 13 | Relocate boxes in room 110 | * | 118.42 | 118.42
| 15 | Connect fan coil & condensing unit | * | 637 | 637
| 16 | Mount cooling tower and reroute | * | 718 | 718 | (not to exceed)
| 17 | Connection for air compressor | * | 191 | 191
| 18 | 110V circuit for elevator control | * | 228 | 228 |  | 0
| 19 | 3 circuits on roof | * | 627 | 627 | (not to exceed)
| 20 | 3 extra circuits from panel to roof | * | 234 | 234
| 21 | Wiring for partitions and UPS | * | 4255 | 4255
| 23 | Fire alarm revisions | * | 5321 | 5321
| 24 | Outlet for telephone from UPS | * | 291 | 291
| 25 | Control switch and wiring for fan | * | 348 | 348
| 26 | Fixtures in stairwell | * | 272 | 272
| 27 | Terminations to furniture partition | * | 51 | 51 |  |  | Edwards
| 28 | UPS, fire alarm, phone, Alcan fix | * | 769.57 | 769.57
| 29 | Chiller control field wiring | * | 700 | 700
Clean up credit
|  | TOTAL |  | 33759.08 | 33759.08 | 0
Mohawk
|  | Pad in basement | * | 493.05 |  | 493.05
| 1 | Gravel, bobcat operator & concrete | * | 835 |  | 835
| 2 | 3 finishers - 6 hrs each | * | 729 |  | 729
| 3 | Pea gravel & 2 finishers - 2 hrs | * | 522 |  | 522
| 4 | Concrete pad in baesment | * | 472 |  | 472
| 5 | Conveyor - 1/2 day | * | 550 |  | 550
| 6 | Conveyor - 1/2 day | * | 600 |  | 600 | 0
| 7 | Conveyor - 1/2 day | * | 400 |  | 400
| 8 | Floor refinishing | * | 3417.5 |  | 3417.5
| 9 | Extras as agreed 1/8/91 | * | 9500 |  | 9500 |  | Vaughn
|  | TOTAL |  | 17518.55 | 0 | 17518.55 |  | Fran & Asso
|  | Capitol Glass |  |  |  |  | 0 | Waco
| 1 | Low E glass-west and south | * | 2149 | 2149 |  |  | Vaughn
| 2 | Mitered returns | * | 1665 | 1665 |  |  | Mohawk
| 3 | "J" 2nd order 48 +15 glass stop | * | 129 | 129 |  |  | Vaughn
| 4 | One (1) blank cylinder | * | 92 | 92 |  |  | Ruben
| 5 | Remove and reinstall atrium glass | * | 500 | 500
| 6 | Rebuild cutout for electric strike | * | 900 | 900 |  | 880
| 7 | Remove & reinstall 2nd floor windows | * | 500 | 500 |  |  | Ruben
| 8 | Remove damaged mullion | *562 | 562 | 562
| 9 | Revision of #7-accept additional | * | 250 | 250
0
|  | TOTAL |  | 6747 | 6747 | 0
Valley Automatic Sprinkler
| 1 | 60 suspended heads in basement | * | 2100 | 2100
| 2 | Connect to old building | * | 2470 | 2470
| 3 | Adjust height of basement sprinklers | * | 1000 | 1000
|  | TOTAL |  | 4570 | 4570 | 0
Hendersons' Construction
| 1 | Setting door frames |  | 1872 | 1872
| 2 | Repair wall at corner F5 |  | 392 | 392
| 3 | Move wall at stair #3 2" |  | 720 | 720
| 4 | Moving west wall of elec rm 2' east |  | 550 | 550
| 5 | Cutting concrete & slab at elevator |  | 468 | 468
| 6 | Repair block by steel beam 2E |  | 360 | 360
| 7 | "16" extra brick |  | 900 | 900 |  | 0
| 8 | Misc extra |  | 3300 | 3300
| 9 | repair & set doors |  | 768 | 768
| 10 | 5 rools plastic seal |  | 313.5 | 313.5
|  | TOTAL |  | 9643.5 | 9643.5 | 0
|  | R & G Interiors (Exterior) |  |  |  |  | 0
| 1 | Revise at north stairwell | * | 400 | 400
| 2 | Saturday overtime | * | 400 | 400
| 3 | Panzer mesh | * | 585 | 585
| 4 | Patch exterior Dryvit | * | 178 | 178
|  | TOTAL |  | 1563 | 1563
R & G Interiors (Interior)
| 1 | Personnel dept wall | * | 358.75 | 358.75
| 2 | Extra walls in kitchen & lunchroom | * | 503.4 | 503.4
| 3 | Credit for Capitol Glass charge | * | -1000 | -1000
| 4 | Drywall in stairwell and coffee room | * | 229.4 | 229.4
| 5 | Door in president's office | * | 109.1 | 109.1
| 6 | Framing under stairwell #1 | * | 158.65 | 158.65
| 7 | Revise #3-credit to be $500 | * | 500 | 500
| 8 | Double row of studs on atrium soffit | * | 376.5 | 376.5
| 9 | Frame & drywall soffits in hall | * | 593.65 | 593.65
|  | TOTAL |  | 1829.45 | 1829.45
Edwards Engineering
| 1 | Elevator exhaust | * | 901 | 901
| 3 | T & M for gas pipeline | * | 552 | 552
| 2 | Training room per discussion | * | 6695 | 6695 |  | 0
| 4 | Gas piping | * | 2777 | 2777
| 5 | Skylight area ductwork revision | * | 478 | 478
| 6 | Huymidifidation boiler flue stack | * | 184 | 184
| 7 | S1 & ER1 ductwork revision | * | 2000 | 2000
| 8 | Rerouting fan coil ductwork on 2nd | * | 256 | 256
0
| 9 | Flow switch installation | * | 138 | 138
|  | Generator cooling radiator inst |  |  | 0
| 10 | Credit for damaged mullion (Capitol) | * | -562 | -562
| 11 | Emergency generator remote piping | * | 1793 | 1793
| 12 | Scotts changes to Art's Area |  | 292 | 292
| 13 | Paint EVASE credit |  | -250 | -250
| 14 | Delete air leak test |  | -454 | -454
| 15 | Delete Air Leak Test |  | -1000 | -1000
| 16 | Stained Tile Credit |  | -250 | -250
| 17 | Move grill in NW Hall not CAE |  | 212 | 212
|  | TOTAL |  | 13762 | 13762 | 0
Imperial
0
Knoll Steel
|  | Miscellaneous - Call Kenny |  | 295
|  | Set stack |  | 1535
|  | Stairwell |  | 1920
|  | TOTAL |  | 3750 | 0 | 0
Gritschke Engineering
|  | Generator, elevator room exhaust |  | 1170
Norman Security
| 1 | 150 security cards | * | 1035 | 1035
|  | TOTAL |  | 1035 | 1035 | 0
Campbell Decorating
| 1 | Cut in drop ceiling on 2nd floor | * | 700 | 700
| 2 | Labor & materials for lab floors | * | 800 | 800
| 3 | Finish carpeted areas by 3/13/91 | * | 400 | 400
| 4 | Epoxy paint in rooms 143,144,151 | * | 1000 | 1000
| 5 | Repair of walls around doors | * | 700 | 700
| 6 | Hang additional wallpaper | * | 936 | 936
| 7 | Repair of wallpaper around doors | * | 1200 | 1200
| 8 | Feather drywall in conference room | * | 160 | 160
| 9 | Credit for damaged kitchen tile | * | -90 | -90
|  | TOTAL |  | 5806 | 5806
Dimensional Flooring
| 1 | Ceramic tile prep work | * | 524 | 524
| 2 | Polished tile for entry area | * | 597 | 597
| 3 | Repair tile in women's washroom | * | 106.25 | 106.25
| 4 | Install treads on main stairway | * | 1031 | 1031
| 5 | Resilient floor preparation | * | 1037.5 | 1037.5
| 6 | Replace damaged kitchen tile | * | 90 | 90
|  | TOTAL |  | 3385.75 | 3385.75 | 0
Hire-Nelson
| 1 | Base cabinets in conference room | * | 1709 | 1709
| 2 | Fabric for reception desks | * | 94 | 94
| 3 | Wall cap and base and chair rail | * | 1400 | 1400
|  | TOTAL |  | 3203 | 3203 | 0
Noonan-Sullivan
| 1 | Additional 30 feet of Alcan ceiling | * | 250 | 250
| 2 | Class A tile in basement | * | 5550 | 5550
|  | TOTAL |  | 5800 | 5800 | 0
Dover
|  | Dover back charge to L&G Compressor |  | 125 | 125
Northern Carpet
| 1 | Floor prep | * | 300 | 300
| 2 | Basement carpet | * | 4907 | 4907
| 3 | 864 ft cove base for basement | * | 903.31 | 903.31
| 4 | Floor patch for basement | * | 150 | 150
|  | TOTAL |  | 6260.31 | 6260.31 | 0
Landis & Gyr
| 1 |  |  | -784
| 2 |  |  | -380
| 3 |  |  | -125
| 4 |  |  | 450
| 5 |  |  | -3500
| 6 |  |  | -125.6
7
8
9
|  | TOTAL |  | -4464.6 | 0

## Buildings punch list
0 |  | Video Conference Plan
0
0 |  | Lab Sample Door lock
0 | Not Poss. | Lunchroom door lock protector plate like main door
0 |  | Balance Bathroom ventilator fan
0 |  | Do Maintainence Punch Schedule
0 | HVAC T | Separate phone calling devise for cool or wet building
1
1 |  | Check Lab hood Fans
1 |  | Check all Air ducts from VAV and Valve opps
1 |  | Clean and repair Drivit see truck dock. |  | D | Art | Install all Door Hardware 1st floor |  | 1 | D | Pat Wood | Solvent Room ramp |  | 1
1 |  | Sign for Wood street at Quintin |  | D | Capital | Reduce |  | 1 | D | Art | Install all Door Hardware LL |  | 1
1 |  |  |  | D | Capital | Leak outside Rich Kings office |  | 1 | D | Dim Tile | Stair tread Main (cut carpet to fit until mat arrives ) |  | 1
1
2 |  | Cooling Tower Cleaning |  | D | Capital | Lunch Room Lock |  | 1 | D | Pat Wood | Paint prep room corner |  | 1
2 |  |  |  | D | Capital | Fix Leak in South Atrium Window |  | 1 | D | Pat Wood | Perchloric hood wiring |  | 1
2 |  |  |  | D | Dim Tile | Entry floor tile finish |  | 1 | D | Pat Wood | Lunch Room door New Sill & support |  | 1
2 |  | Lab Doors closing quality |  | D | Dim Tile | Lunch Room floor tile repair |  | 1 | D | Pat | Air Leak in Lab 9 @ floor |  | 1
2 | Check for leak | Detail north stairwell and seal top of blocks to roof |  | D | Dim Tile | Stair tread North |  | 1 | D | Pat Wood | Main Entrance Stationary Door Keylock Dead bolts |  | 1
2 |  | Detail all rooms 1 at a time |  | D | Dimen Tile | Repair Tile outside lunch room |  | 1 | D | Pat Wood | Install new Tumblers on 4 door outside doors |  | 1
2 |  | Closet in Board room |  | D | DONE | Bolt Wall above solvent room |  | 1 | D | Pat Wood | Door Latch Guards and auto close Adjustments |  | 1
2 |  | Reveal Fix (doors & Cubicles) |  | D | DONE | Modular furniture hookup |  | 1 | D | Pat Wood | Electric Lock problems with Bolt hold close |  | 1
2 |  |  |  | D | DONE | Paint West stairwell |  | 1 | D | Pat Wood | Cover hole in 1st floor conference rm |  | 1
3 |  | Cooling Tower Water Sieve (see Martin) |  | D | DONE | Pipe Insulation for all vertical drain pipes |  | 1 | D | Pat Wood | Clean Return Air Grills |  | 1
3 |  | Replace or fix stained Ceiling Tile |  | D | DONE | Reset North Door and install Latch wire |  | 1 | D | Larry | Balance air flows S2 |  | 1
3 | Check for opps | Perchloric hood flow analog to program | 2 | D | DONE | Walker duct tombstones |  | 1 | D | Larry | Balance air flows S3 |  | 1
3 |  | Can lights for outside and Atrium Entry | R | D | ED | Unistrut in 1st Floor Conference Room |  | 1 | D | Pat Wood | Closet Door Facia |  | 1
3 | Partial 2002 & 2003 | Old lab roof HVAC unit econimizer | R | D | Jim | Security system UPS outlet |  | 1 | D | Pat Wood | Lunch Room Pipe remove pipe |  | 1
4 |  | Main Door Card Reader |  | D | Northwest | Finish Carpet |  | 1 | D | BoB S | Paint north door inside and out |  | 1
4 |  | Truck Exhaust Fan | 1 | D | Pat Wood | Closet Rods and shelfs see Adele or Carole (Closetmaid) |  | 1 | D | Bob/Wally | Move VAV to Lab 9 |  | 1
4 | PART 2002 | Seal Kitchen Door | 1 | D | Pat Wood | North door closer |  | 1 | D | Carole | Main Door Mat |  | 1
5 |  | Replace Lab Hood Duct on Roof | T | D | Pat Wood | Insulation remove in stairwell heater |  | 1 | D | Bob | Ceiling Stain Causes Janitor Closet |  | 1
5 |  | Heated sample line to Training Room | T | D | Pat Wood | Paint solvent Room |  | 1 | D | Bob | Borrowed light frames |  | 1
5 | Plan | Wrap Pipes from Presidents Bathroom above 1st floor | T | D | Pat Wood | Clean Tile in North Stairwell |  | 1 | D | Bob | Clean Inside Windows Atrium |  | 1
5 |  | 1st Floor Recpetion Area Coat Closet Plan | 1&2 | D | Pat Wood | Elevator Carpet |  | 1 | D | Bob | Redo ceiling tile in 1st floor bathrooms |  | 1
5 |  | Electric Panel Directories | E | D | Pat Wood | HR wall top OAK |  | 1 | D | Bob | Measure air flows ER2 |  | 1
5 |  | Truck dock building protection pier (see Dwg A1) | MR | D | Pat Wood | HD Closer on door near truck dock |  | 1 | D | Bob | Measure air flows ER3 |  | 1
6 |  | Replace Cooling Tower | L | D | WACO | Doghouses for St. Charles hookup in lab 4 |  | 1 | D | Bob | Paint 207 Warehouse Walls and Ceiling |  | 1
6 |  | 207 Roof work and FLASHING over drive in door | MR | D | Art | Perchloric duct leaks under roof |  | 2 | H | Bob/Wally | Stair tread West |  | 1
6 | Done | Easels for all conference rooms | MR | D | Art | Door Hardware 2nd floor |  | 2 | D | DPCM | Duct Noise is excessive even with E1 off on a windy day |  | 2
7 |  | Fix bad grass spots | 1 | D | DONE | Hook up reception desks |  | 2 | D | Pat Wood | Pres Coffee light move to over sink and fill holes |  | 2
7 | PART 2002 | Dirt to fill in behind curbs | 1 & 2 | D | DONE | Install Bathroom Towel dispenser |  | 2 | D | Pat Wood | Prresidents Bathroom install pressure equalizing grill |  | 2
7 |  | Paint Structure and Pipes in MR | NA | D | Done | T & H Hole in Entry Wall |  | 2 | D | Carole/Bob | Shelves for Resource Center |  | 2
7 |  | Repair Brick on 207 | 1 | D | P & P | Toliet and Seat in Bill Walker's off |  | 2 | D | Bob | E1 Condensation--need insulation below roof |  | 2
7 |  | Presidents bathroom clean and fix wallpaper | R | D | Pat Wood | Seal wall at top of stairwells @ Scuttle |  | 2 | D | Bob/Wally | Build shelves in janitors rooms |  | 2
7 | Done | Bathroom fan for 207 | 1 | D | Pat Wood | West stair well seal top of wall |  | 2 | D | Carole/Bob | Media Center for conf rooms |  | 2
8 |  | Connect Steam Boiler | 2 | D | Pat Wood | John's Office finish and move in |  | 2 | D | Vince | UPS and Emergency survey Fix WIW Sue Barb |  | 2
8 | HVAC T | VAV flow adjustment all boxes | B | D | Pat Wood | Johns office |  | 2 | H | Bob/Wally | Skylight tunnel in library |  | 2
8 |  | Clean up mechanical room | R | D | Pat Wood | Perchloric hood stack chase |  | 2 | L | Pat Wood | Finish beam in wall north stairs |  | 2
8 |  | Flag pole | 2 | D | R & G | Mud around outlets |  | 1 & 2 | D | Bob/Wally | UPS for rentals |  | 246
8 |  | Check air flows ER1 w/ red hood & enter on Data sht | 2 | D | Pat Wood | Closet bumpers |  | 1 &2 | D | R & G | Drywall around outlets |  | 1&2
8 |  | Smooth MR floor | MR | D | Pat | Fire doors operational |  | ALL | D | Bill | Rearrange spotlights in pres office |  | 1&2
8 |  | Kim and Traci Computer & Phone on UPS | R | D | Bill | Connect Fire Alarm to Fire Dept |  | B | D | Pat Wood | Catwalk above metal ceiling |  | 1&2
9 |  | Volleyball court improvements | 2 | D | Electric | Wire generator fan control system |  | B | D | Pat Wood | CAE must install catwalk over metal ceiling |  | 1&2
8 |  | Install handrails on test platform | T | D | Pat Wood | Extra Electric in Dept 61 Area |  | B | D | Pat Wood | Generator Radiator |  | AW
9 |  | Install test platform 50#/ft2 | T | D | Pat Wood | Paint Archive room |  | B | D | WACO | Basement ceiling lights |  | B
9 |  | Rig Unistrut gantry to enable lift from truck dock | 1 | D | Done | Air Dryer for labs |  | D | D | DPCM | Leaks in Wall in sprinkler room |  | B
9 |  | Sample spiking port | MR | D | DONE | Air Seperator knurled missing |  | D | D | Pat Wood | Air Filter section Missing |  | B
9 |  | Steps for test plateform. | 3 | D | Done | Check hood flows |  | D | D | Bob/Wally | Cool Electrical room |  | B
9 |  | Test ports in horizonal and vertical ducts | 1 | D | Done | Door latch problem at main entrance |  | D | D | Bob/Wally | Caulk around East Area Well Door and Fill Rad Holes |  | B
9 |  | Trap door for storage under grating in hung box | MR | D | Done | Elevator Sump pump lower level switch |  | D | D | Bob/Wally | Work Area Setup for Electrical in Electical rm |  | B
9 |  | Cut fan pads to size | 1 | D | Done | Fire control system test |  | D | D | Bob/Wally | Work Area Setup Carpentry just outside MR |  | B
9 |  | Mech room fixup | MR | D | DONE | Fix air compressor leak |  | D | D | Bob | Greenfield on S3 leads and Wire to outside Rad |  | B
9 |  | Paint Structure in MR | MR | D | Done | Grind spatter off stairwell wall |  | D | D | Bob/Wally | Archive build shelves plan 1st |  | B
D |  | Run wire from MR to SCU 3 & 4 | ALL | D | Done | Hang Unit heater for generator |  | D | D | Bob | Build shelves in archive room per plan |  | B
D | Done | Dry Mark boards for conference rooms 1 & 2. | MR | D | Done | Landscape trash out of dumpster |  | D | D | Bob/Wally | 207 Roof work at East end |  | E
D |  | Door Stops instead of blocks or Hinge Breaker | All | D | Done | Leak check compressed air lines |  | D | D | Bob/Wally | Seal truck dock conduit where jack removed light |  | E
D |  | CFM w/ current transformer on E3 | 1 | D | Done | Wire Bachco 4/25 |  | D | D | Bob | Paint 207 walls |  | E
D |  | Control for S1HWT | MR | D | Done | Wire lab 9 |  | D | H | Fran | fence on old building above entrance |  | E
D | HVAC T | Energy Saving Thermostats or add to Landis & Gyr(all) | R | D | DONE | Wire west oven 4/12 deadline |  | D | D | Pat Wood | Wire north wall lab 9 plastic plug mold for UPS |  | L
D | HVAC T | Magnihelics for S1, S2, S3 & ER1 | 1&2 | D | P & P | Hotwater ON |  | D | D | Edwards | Fix Leaks in Hood Exhaust system |  | L
D | HVAC T | Plan for Cooling Warehouses | 1 | D | WACO | Seal pipes in mechanical room "Guaranteed" |  | D | D | Pat Wood | Lab 4 Plywood PAINT BEFORE INSTALLING! DON'T Paint epoxy walls! |  | L
D | HVAC T | AC duct to phone closet plan | 1 | C | Pat Wood | Purchase and Install new door in Boyle area |  | E | D | Larry | Set Hood Min flows E1 |  | L
D | Alex | AA and ICP Flow total in Computer | O | D | Pat Wood | Dumpster Pad and cedar fence |  | E | D | Bob/Wally | Adjust lab hood sash's |  | L
D | Bob | Purchase and Install new door in Boyle area | MR | D | Pat Wood | Conference room chair rails and floor molding |  | E | D | Larry | Balance air flows S1 |  | L
D | HVAC T | Warehouse Cooling improvement plan | L | D | Pat Wood | 207 Air Conditioning Condenser fan |  | ER | D | Bob/Wally | Data conduit to 246 |  | LL
D | HVAC T | Measure E1 Air Volume with Current Transformer | L | D | DONE | Paint and install stairrails in west stairwell |  | I2 | D | Vince | PHONE AND DATA Wire TO RENTALS |  | LL | $$$$$$
D | HVAC T | drawing of generator electric on CADD | MR | D | P & P | Kitchen sink pull downs |  | I2 | D | Bob/Wally | Paint floor in rentals |  | LL
D | Bob | Thumb Lock to LIBRARY and conference S. door | MR | D | Campbell | Paint 1st floor Closet Door Frames Grey |  | l | D | Pat Wood | Pipe Cover labels |  | MR
D | Done | Sound proof elevator, sprinkler and Mech rooms | MR | D | Carole | Lab 9 countertop |  | l | D | Bill | Current Transformers |  | MR
D | HVAC T | Training room air flow VAV and valve |  | D | Carole | Lunch Room vending machines |  | l | D | Pat Wood | Air Compressor on Emergency Generator |  | MR
D | HVAC T | Freeze protection program on building computer | O | D | Edwards | Lab 5 Return |  | L | D | Pat wood | Install current transformer on E1 |  | MR
D | Bob | Check all fans for vibration | O | D | Pat Wood | Wire north wall lab 9 for 220 1ph from Emer Gen Sw |  | L | D | Pat wood | Install current transformer on ER1 |  | MR
D |  | Check s3 coil for leaks | O | D | Pat Wood | Lab Hall door dust caps |  | L | D | Pat wood | Install current transformer on E3 |  | MR
D | HVAC T | Move dept 61 fan switch and install thermostat | 2 | D | Pat Wood | Paint Plug Mold |  | L | D | Larry | Condenser pump shutoff overflow problem. |  | MR
D | Bob | Crate cooling coil | LL | D | Pat Wood | DI water for labs |  | L | D | Bob/Wally | Install SP gauge on ER1 duct in MR |  | MR
D | HVAC T | Humming noise on Board room VAV at 100% S3 | MR | D | Pat Wood | AA hoods installation and L & G prog mod |  | L | D | Bob/Wally | Insulate concrete in Inlet Air Plenum MORE ON FOOTING |  | MR
D | HVAC T | Hotwater room ventilation |  | D | St. Charles | Cracked Sashes in Labs |  | L | D | Edwards | BOILER FILL and Presure Problem |  | MR
D | HVAC T | CFM w/ current transformer on ER1 (S of PDSA) |  | D | Bill | Chiller startup |  | MR | D | Bob/Wally | Roll steam boiler back 6" toward wall ALIGN |  | MR
D | DONE | Fix Hinges on Wood Street door |  | D | DONE | buy valves for MR water |  | MR | D | Bob/Wally | Boiler relief valves should be piped to drains Lets let this go until Presure relief problem is fixed. | MR | MR | 1991-05-24
|  |  |  | D | DONE | Cut around S3 leak with Drummel |  | MR | D | Bob/Wally | Bent linkage S1 OA damper west |  | MR
|  |  |  | D | DONE | Flush Chiller lines |  | MR | D | Bob/Wally | Clean Equip S1-3/ Steam Boiler /Hotwater tank/Gen |  | MR
|  |  |  | D | Done | Hook up Elect for water treatment |  | MR | D | Bob/Wally | Clean out sump and settling holes. |  | MR
|  |  |  | D | DONE | Leak in S3 coil |  | MR | D | Bill W | Boiler lead lag control |  | MR
|  |  |  | D | Edwards | Access to grease fan bearings |  | MR | D | Bob/Wally | Fix ABB S2 Drive |  | MR
|  |  |  | D | Ewdards | Signs for piping in MR |  | MR | S | Bob | Boiler modulating control |  | MR
|  |  |  | D | Hi Tech | Install water treatment chemicals |  | MR | S | Bob | Install Gaskets for Damper blades |  | MR
|  |  |  | D | P & P | Sanitary pump leaks |  | MR | S | Jim | Balance water flow check |  | MR
|  |  |  | D | P & P | Sump pump leak |  | MR | D | Pat Wood | Gas Pipe Line. on drawing? |  | NA
|  |  |  | D | Pat Wood | Chilled water leak in S3 pipe |  | MR | D | Bob/Wally | Cart for new building |  | NA
|  |  |  | D | Pat Wood | Stack drain with 4" water seal SS to froor drain |  | MR | D | Jim & Vince | Audio Paging System |  | NA
|  |  |  | D | Pat Wood | Area well drain pipes install cover plates on all 3 |  | MR | D | Vince | UPS power audit and plan |  | NA
|  |  |  | D | Pat Wood | Water treatment relay on chiller contact 11 |  | MR | D | Vince | Emergency power audit and plan |  | NA
|  |  |  | D | Pat Wood | Water treatment interlock with condenser flow |  | MR | D | Pat Wood | Install grating over east area well |  | O
|  |  |  | D | WACO | Rewire ABB drive control wires |  | MR | D | Carole/Pat | Paint Visitor on 4 Parking Spaces |  | O
|  |  |  | D | Adele | Landscaping bids |  | NA | D | ED | Patio wall flashing on outside of window wall |  | O
|  |  |  | D | Dover | Elevator oil leak |  | NA | D | Pat Wood | Leaks in MR wall near sumps |  | O
|  |  |  | D | Pat Wood | Clean elevator except carpet |  | NA | D | Pat Wood | Spread Straw |  | O
|  |  |  | D | CAE | Order landscaping |  | O | D | Bill | Window clean outside entry |  | O
|  |  |  | D | DONE | Conduit before Fill behind curbs |  | O | D | Pat Wood | Soil pipe drain on west foundation wall |  | O
|  |  |  | D | Landscaper | Protect maple tree |  | O | D | Bob/Wally | Remove old Electrical Box by Entrance transformer |  | O
|  |  |  | D | Pat Wood | Clean up behind curbs, around well and in pond. |  | O | D | Bob/Wally | Caulk Expansion joints |  | O
|  |  |  | D | Pat Wood | Before landscaping cleanup |  | O | D | Bob/Wally | Power conduit to trailers |  | O
|  |  |  | D | Pat Wood | Fill front for sidewalk |  | O | D | Green Rose | Replace Dead Trees |  | O
|  |  |  | D | Pat Wood | Elevate man hole covers |  | O | H | Bill | Patch holes in parking catch basins |  | O
|  |  |  | D | Pat Wood | Truck Dock Drain Screen |  | O | L | Bill | Fix brick problems. |  | O
|  |  |  | D | RG | Repair dryvit |  | O | D | Pat Wood | Insulate E1 inlet plenum and install Dam |  | R
|  |  |  | D | Spinolas | Finish topsoil |  | O | D | Pat Wood | Set PRE1 volume and speed |  | R
|  |  |  | D | Spinolas | Remove Concrete from wood st shoulder |  | O | D | Bill | Stack Engineering calcualtions to village |  | R
|  |  |  | D | Spinolas | Remove old curb and asphalt |  | O | D | Pat Wood | Aim East Flood light or move |  | R
|  |  |  | D | DONE | Prepare Air Well for Lift truck Delivery |  | PW | D | Pat Wood | Seal Concrete block above patrition wall & paint |  | R
|  |  |  | D | Art | Perchloric duct leaks above roof |  | R | D | Pat Wood | Flashing cover on south wall |  | R
|  |  |  | D | DONE | Fan Noise in E1 |  | R | D | Bob/Wally | 207 fix HVAC heat and Ac |  | R
|  |  |  | D | DONE | Fix latch on roof hatch |  | R | D | Bob/Wally | Paint Structure on roof & Pipes |  | R
|  |  |  | D | Done | Main Stack and Fan touchup |  | R | H | Hold | Replace Rectangular Duct with Round 36" Dia |  | R
|  |  |  | D | Done | Paint touch up stack and E1 fan |  | R | L | Pat Wood | Fix hole in membrane roofing |  | R
|  |  |  | D | PAt | Cooling Tower Fill Valve |  | R | D | Pat Wood | Laundry Tub Drain hook up |  | SR
|  |  |  | D | Pat Wood | Cooling tower cleanup and hatch cover |  | R | D | Bob | Roof protection under scaffolding |  | T
|  |  |  | D | Pat Wood | Cooling Tower fix leaks |  | R | D | Pat Wood | Clean roofs
|  |  |  | D | Pat Wood | Fan Noise e3 or E1 |  | R | D | Bob | Fix S3 Chilled water coil
|  |  |  | D | Pat Wood | Cooling Tower fix Float Valve |  | R | D | Bob | West man door sticks
|  |  |  | S | Larry & Joe | Chiller Automation and restart after outage
|  |  |  | S | Mark Roach | Hinge grating over east area well |  | O | L | Pat Wood | Lunch Room Base trim
|  |  |  | D | Bob | Paint truck doors |  | 1 | D | Bob | Ceiling Tile fix after Edwards Fixes Staining problem |  | 1
|  |  |  | D | Bob | Patch area well drain pipe |  | MR | D | Bob | Welder outlet in MR |  | MR
|  |  |  | D | Liz | Screen to seperate training room from Weeze & Walts |  | B | D | Bob | MR Bolt dampers open in S1, S2, S3 |  | MR
|  |  |  | D | Bob | Paint 207 bathroom and clean fix tile |  |  | D | Bob | Redo Downlights in presidents office |  | 2
|  |  |  | D | Bob | Make Main Stair Risers more equal |  |  | S | Bob | Interference in mechanical room |  | MR
|  |  |  | D | Bob | Sky Light in Library (drop in grid) | Add 2 more panels |  | S | Bob | Roof Problems |  | R
|  |  |  | D | Bob | 207 and clean tile floor and walls |  |  | D | Bob | Window mullun to wall gap filler (Jerry Murray's Office) |  | 1& 2
|  |  |  | D | Bob | Work Area Setup for Mechanical in MR |  |  | D | Bill | Boilers should alternate |  | MR
|  |  |  | D | Bob | Work Area Setup for welding in MR |  |  | D | Bob | Grout Pumps |  | MR
|  |  |  | D | Bob | Truck Dock Angle |  |  | D | Bob | Truck dock building protection pier |  | O
|  |  |  | D | Bob | Remove grating to paint steel then replace |  |  | D | Bob | Tar on Wall above Drive in Door |  | R

## hot Days
Relative Benefit | Energy Saving Idea for Hot Days | Relative Savings $/Mo. | Relative Costs $/Mo. | Task Owner >Trainer | Auditor | Plan & Procedure | Tag needed | Reverse (when how)
50 | If lab work can be delayed turn off chilled water to lab fan S1 coil | 500 | 10 | Doug>Vince | Bill |  | On Lab Doors | Program HVAC
20 | Close Blinds and pull all shades down | 200 | 10 | Team>Vince
10 | Raise unused lab room temperature set points | 50 | 5 | Doug>Vince | Bill
10 | Reduce Lighting | 100 | 10 | Vince
6 | Reduce HAVC fan speeds by lowering SP | 30 | 5 | Bill | Vince
5 | Set Thermostats up 2 degrees | 100 | 20 | Team>Vince
5 | Replace spot lights with more energy efficient ones | 50 | 10 | Dan
2 | Seal off Lab hoods which are not in use | 100 | 50 | Doug/Bill
2 | Flood & Spray Roofs and outside walls using well water | 200 | 100 | Dan
2 | Minimize shades and blind chimney effect | 50 | 25 | Needs a plan
2 | Shut off unused office equipment | 20 | 10 | Team>Vince
2 | Reduce boiler hot water temperature | 10 | 5 | Dan
1 | Drape or shade atrium windows with reflective material | 200 | 200 | Needs a plan
1 | Weather strip and adjust doors seal | 100 | 100 | Needs a plan
1 | Seal Roof openings which are not in use (roof fan, space heater etc.) | 100 | 100 | Doug>Vince | Bill
1 | Turn off hot water heaters | 5 | 5 | Dan
1 | Use stairs | 1 | 1 | Need script & announcement
0.5 | 3M film on single pane windows | 50 | 100 | Needs a plan
0.5 | 500 ww Bathroom vent fans on light switch | 50 | 100 | Needs a plan
0.5 | Replace lights with more energy efficient ones | 50 | 100
0.2 | Cover sky lights with reflective material | 30 | 150 | Needs a plan
0.02 | Seal north stairwell | 1 | 50
0.005 | Install reflectors to improve light effectiveness | 50 | 10000 | Needs a plan
| Total monthly savings estimate | 2047
| Total yearly savings estimate | 8188
| Net Presenty Value | 49156.5368
Long Range Energy Saving Idea for Hot Days
0.1 | Plant shade trees | 0.1
Install More insulation
Replace lights with more energy efficient ones
Install reflectors to improve light effectiveness
Paint walls white
Install some operable windows
Install motion detector light switches
Install motion detector thermostats
Plant Ivy on brick walls

## Curtailment
Energy Saving Ideas for Curtailment
Do Items on Hot Days list
Throw Auto Transfer breaker
Throw Manual Breaker (study what is on it)
Emergency lights except HVAC duct smoke alarm
Turn off boilers
Turn off unneeded pumps
Switch more load to emergency generator
Run extra generators for 212 and 207
Run only one fan or reduce speed on 207 cooling coil

## Gas Prices
MCWCCITY = Midwest - Chicago Citygate
Trade Date Issue Date MCWCCITY
2003-12-15 | 2003-12-16 | 6.66
2003-12-16 | 2003-12-17 | 6.56
2003-12-17 | 2003-12-18 | 6.56
2003-12-18 | 2003-12-19 | 6.94
2003-12-19 | 2003-12-22 | 6.74
2003-12-22 | 2003-12-23 | 6.2
2003-12-23 | 2003-12-24 | 5.45
2003-12-24 | 2003-12-29 | 5.42
2003-12-29 | 2003-12-30 | 5.54
2003-12-30 | 2003-12-31 | 6.02
2003-12-31 | 2004-01-05 | 5.86
2004-01-05 | 2004-01-06 | 6.64
2004-01-06 | 2004-01-07 | 7.02
2004-01-07 | 2004-01-08 | 6.56
2004-01-08 | 2004-01-09 | 6.42
2004-01-09 | 2004-01-12 | 6.81
2004-01-12 | 2004-01-13 | 5.99
2004-01-13 | 2004-01-14 | 6
2004-01-14 | 2004-01-15 | 5.76
2004-01-15 | 2004-01-16 | 5.98
2004-01-16 | 2004-01-20 | 5.58
2004-01-20 | 2004-01-21 | 6.1
2004-01-21 | 2004-01-22 | 6.27
2004-01-22 | 2004-01-23 | 5.99
2004-01-23 | 2004-01-26 | 5.94
2004-01-26 | 2004-01-27 | 5.82
2004-01-27 | 2004-01-28 | 6.06
2004-01-28 | 2004-01-29 | 6.57
2004-01-29 | 2004-01-30 | 6.17
2004-01-30 | 2004-02-02 | 5.8
2004-02-02 | 2004-02-03 | 5.49
2004-02-03 | 2004-02-04 | 5.75
2004-02-04 | 2004-02-05 | 5.82
2004-02-05 | 2004-02-06 | 5.59
2004-02-06 | 2004-02-09 | 5.43
2004-02-09 | 2004-02-10 | 5.5
2004-02-10 | 2004-02-11 | 5.39
2004-02-11 | 2004-02-12 | 5.32
2004-02-12 | 2004-02-13 | 5.35
2004-02-13 | 2004-02-17 | 5.59
2004-02-17 | 2004-02-18 | 5.31
2004-02-18 | 2004-02-19 | 5.24
2004-02-19 | 2004-02-20 | 5.24
2004-02-20 | 2004-02-23 | 5.19
2004-02-23 | 2004-02-24 | 5.07
2004-02-24 | 2004-02-25 | 5.01
2004-02-25 | 2004-02-26 | 5.07
Notes : Prices are in U.S. $/MMBtu dry gas. Prices are for gas traded on the dates shown for incremental delivery.

## CILCO data 02
Customer Projected Savings Analysis
12 Month Comparison
24 Month Offer: June 2002 - May 2004
Clean Air Engineering
Account # | 0291770002
500 West Wood Street
Palatine, IL
Delivery Services Tariff (DST)
Month | Total kWh | Demand (kW) | ComEd Rate 6 Charges | Delivery Services | Transmission | Customer Transition Charge (CTC) | Total ComED DST Charges | CILCO Energy Supply | TOTAL DELIVERED COST | Savings with CILCO
2004-10-02 | 54540 | 227.3 | 4533.7444 | 835.668 | 174.528 | 1322.0496 | 2332.2456 | 1908.9 | 4241.1456 | 292.5988
2004-11-02 | 51832 | 205.572 | 4211.9534 | 760.4891 | 165.8624 | 1256.4077 | 2182.7592 | 1814.12 | 3996.8792 | 215.0742
2004-12-02 | 57308 | 146.544 | 3744.1642 | 556.2522 | 183.3856 | 1389.1459 | 2128.7838 | 2005.78 | 4134.5638 | -390.3995
2005-01-02 | 63689 | 143.54 | 3913.6184 | 545.8584 | 203.8048 | 1543.8214 | 2293.4846 | 2229.115 | 4522.5996 | -608.9811
2005-02-02 | 53883 | 143.82 | 3606.104 | 546.8272 | 172.4256 | 1306.1239 | 2025.3767 | 1885.905 | 3911.2817 | -305.1777
2005-03-02 | 53929 | 141.67 | 3584.2056 | 539.3882 | 172.5728 | 1307.239 | 2019.2 | 1887.515 | 3906.715 | -322.5093
2005-04-02 | 49785 | 138.1 | 3414.1847 | 527.036 | 159.312 | 1206.7884 | 1893.1364 | 1742.475 | 3635.6114 | -221.4267
2005-05-02 | 69783 | 258.18 | 5351.936 | 942.5128 | 223.3056 | 1691.5399 | 2857.3583 | 2442.405 | 5299.7633 | 52.1726
2006-06-02 | 72333 | 257.68 | 6209.4146 | 940.7828 | 231.4656 | 298.7353 | 1470.9837 | 4484.646 | 5955.6297 | 253.7849
2006-07-02 | 80217 | 276.06 | 6714.5505 | 1004.3776 | 256.6944 | 331.2962 | 1592.3682 | 4973.454 | 6565.8222 | 148.7283
2006-08-02 | 84929 | 302.69 | 7233.8897 | 1096.5174 | 271.7728 | 350.7568 | 1719.047 | 5265.598 | 6984.645 | 249.2447
2006-09-02 | 83271 | 273.01 | 6768.8811 | 993.8246 | 266.4672 | 343.9092 | 1604.201 | 5162.802 | 6767.003 | 1.878
2006-10-02 | 54540 | 227.3 | 4533.7444 | 835.668 | 174.528 | 225.2502 | 1235.4462 | 1908.9 | 3144.3462 | 1389.3982
2006-11-02 | 51832 | 205.572 | 4211.9534 | 760.4891 | 165.8624 | 214.0662 | 1140.4177 | 1814.12 | 2954.5377 | 1257.4157
2006-12-02 | 57308 | 146.544 | 3744.1642 | 556.2522 | 183.3856 | 236.682 | 976.3199 | 2005.78 | 2982.0999 | 762.0644
2007-01-02 | 63689 | 143.54 | 3913.6184 | 545.8584 | 203.8048 | 263.0356 | 1012.6988 | 2229.115 | 3241.8138 | 671.8047
2007-02-02 | 53883 | 143.82 | 3606.104 | 546.8272 | 172.4256 | 222.5368 | 941.7896 | 1885.905 | 2827.6946 | 778.4094
2007-03-02 | 53929 | 141.67 | 3584.2056 | 539.3882 | 172.5728 | 222.7268 | 934.6878 | 1887.515 | 2822.2028 | 762.0029
2007-04-02 | 49785 | 138.1 | 3414.1847 | 527.036 | 159.312 | 205.6121 | 891.96 | 1742.475 | 2634.4351 | 779.7496
2007-05-02 | 69783 | 258.18 | 5351.936 | 942.5128 | 223.3056 | 288.2038 | 1454.0222 | 2442.405 | 3896.4272 | 1455.5088
Total | 775499 | 302.69 | 59286.6467 | 9289.5344 | 2481.5968 | 3202.8109 | 14973.942 | 35802.715 | 50776.657 | 8509.9897
|  | Cents per kwh | 7.645 | 1.1979 | 0.32 | 0.413 | 1.9309 | 4.6167 | 6.5476 | 1.0974
Analysis is based upon the anticipated start date of: May 21, 2002 | [6 empty] | 5044.1688 |  | Percent Savings | 14.35%
|  |  |  | CILCO Energy | Summer Price | Winter Price |  | 8.5
[5 empty] | 6.2 | 3.5
Note
...The above analysis is based on the ComEd Market Index methodology for calculating the Period A (2001) market values and CTC values.
...The analysis is also based on historical data billing periods. Applicable taxes and ComEd decommissioning adjustments are excluded.
Confidential

## Elect Pwr
http://www.comedpowerpath.com |  |  |  |  | http://www.comedpowerpath.com/PowerPathDr/Fa_default.asp
Account # | 291770002 |  |  | Meter # | 091489639 | (add a 0 in front of 9) |  |  | CILCO+ComEd |  | Total 12 M
|  | Period |  | TotalKWH | Rolling 12m | Rolling 12m | Daily Uasge | Rolling 24m | Rolling 24m | ComEd | CILCO | Total | Cost $ | Average MWH
| Period | Days | Demand(KW) | Usage | Average KWH | over 365 days | KWH | Average KWH | over 365 days | Charges | Charges | Charges | Trailing 12 Mo | Trailing 12 Mo
| 1998-07-22 | 33 | 292.872 | 97711 |  |  | 2960.9394 |  |  | 8113.17 |  | 8113.17
| 1998-08-20 | 29 | 274.872 | 88356 |  |  | 3046.7586 |  |  | 7501.73 |  | 7501.73
| 1998-09-21 | 32 | 287.412 | 88165 |  |  | 2755.1562 |  |  | 7674.93 |  | 7674.93
| 1998-10-20 | 29 | 240.204 | 57248 |  |  | 1974.069 |  |  | 5130.64 |  | 5130.64
| 1998-11-18 | 29 | 213.1 | 52864 |  |  | 1822.8966 |  |  | 4668.64 |  | 4668.64
| 1998-12-21 | 33 | 132.34 | 55076 |  |  | 1668.9697 |  |  | 3841.75 |  | 3841.75
1 | 1999-01-22 | 32 | 133.752 | 58217 |  |  | 1819.2812 |  |  | 3944.82 |  | 3944.82
2 | 1999-02-22 | 31 | 140.952 | 55666 |  |  | 1795.6774 |  |  | 3804.14 |  | 3804.14
3 | 1999-03-23 | 29 | 136.84 | 52656 |  |  | 1815.7241 |  |  | 3805.17 |  | 3805.17
4 | 1999-04-21 | 29 | 136.55 | 52283 |  |  | 1802.8621 |  |  | 3788.47 |  | 3788.47
5 | 1999-05-20 | 29 | 234.3 | 61635 |  |  | 2125.3448 |  |  | 5222.33 |  | 5222.33
6 | 1999-06-21 | 32 | 266.08 | 73064 | 66078.4167 | 2170.9541 | 2283.25 |  |  | 6825.02 |  | 6825.02 | 64320.81 | 66.0784
7 | 1999-07-21 | 30 | 262.61 | 82059 | 64774.0833 | 2128.1013 | 2735.3 |  |  | 7098.98 |  | 7098.98 | 63306.62 | 64.7741
8 | 1999-08-19 | 29 | 293.39 | 89001 | 64827.8333 | 2129.8672 | 3069 |  |  | 7780.13 |  | 7780.13 | 63585.02 | 64.8278
9 | 1999-09-20 | 32 | 248.69 | 70873 | 63386.8333 | 2082.5243 | 2214.7812 |  |  | 6496.41 |  | 6496.41 | 62406.5 | 63.3868
10 | 1999-10-19 | 29 | 211.044 | 54903 | 63191.4167 | 2076.104 | 1893.2069 |  |  | 4718.92 |  | 4718.92 | 61994.78 | 63.1914
11 | 1999-11-17 | 29 | 216.04 | 53531 | 63247 | 2077.9302 | 1845.8966 |  |  | 4725.65 |  | 4725.65 | 62051.79 | 63.247
12 | 1999-12-20 | 33 | 142.404 | 58917 | 63567.0833 | 2088.4463 | 1785.3636 |  |  | 4092.95 |  | 4092.95 | 62302.99 | 63.5671
13 | 2000-01-21 | 32 | 154.61 | 63429 | 64001.4167 | 2102.7159 | 1982.1562 |  |  | 4495.87 |  | 4495.87 | 62854.04 | 64.0014
14 | 2000-02-21 | 31 | 161.03 | 62974 | 64610.4167 | 2122.7242 | 2031.4194 |  |  | 4490.43 |  | 4490.43 | 63540.33 | 64.6104
15 | 2000-03-21 | 29 | 221.99 | 60551 | 65268.3333 | 2144.3395 | 2087.9655 |  |  | 4554.32 |  | 4554.32 | 64289.48 | 65.2683
16 | 2000-04-19 | 29 | 215.064 | 58116 | 65754.4167 | 2160.3094 | 2004 |  |  | 4383.4 |  | 4383.4 | 64884.41 | 65.7544
17 | 2000-05-19 | 30 | 258.18 | 69783 | 66433.4167 | 2182.6174 | 2326.1 |  |  | 5241.66 |  | 5241.66 | 64903.74 | 66.4334
18 | 2000-06-20 | 32 | 257.68 | 72333 | 66372.5 | 2180.616 | 2260.4062 | 2171.1052 | 2175.7851 | 5756.43 |  | 5756.43 | 63835.15 | 66.3725
19 | 2000-07-20 | 30 | 276.06 | 80217 | 66219 | 2175.5729 | 2673.9 | 2159.1452 | 2151.8371 | 6338.28 |  | 6338.28 | 63074.45 | 66.219
20 | 2000-08-18 | 29 | 303.12 | 84929 | 65879.6667 | 2164.4244 | 2928.5862 | 2154.2214 | 2147.1458 | 6740.64 |  | 6740.64 | 62034.96 | 65.8797
21 | 2000-09-19 | 32 | 274.956 | 83271 | 66912.8333 | 2198.3682 | 2602.2188 | 2147.849 | 2140.4463 | 6528.19 |  | 6528.19 | 62066.74 | 66.9128
22 | 2000-10-18 | 29 | 227.304 | 54540 | 66882.5833 | 2197.3744 | 1880.6897 | 2143.9582 | 2136.7392 | 4209.19 |  | 4209.19 | 61557.01 | 66.8826
23 | 2000-11-16 | 29 | 205.572 | 51832 | 66741 | 2192.7228 | 1787.3103 | 2142.4754 | 2135.3265 | 3969.06 |  | 3969.06 | 60800.42 | 66.741
24 | 2000-12-19 | 33 | 146.544 | 57308 | 66606.9167 | 2188.3176 | 1736.6061 | 2145.2936 | 2138.3819 | 4095.29 |  | 4095.29 | 60802.76 | 66.6069
25 | 2001-01-23 | 35 | 143.652 | 63689 | 66628.5833 | 2189.0294 | 1819.6857 | 2145.3105 | 2145.8727 | 2399.42 | 2241.85 | 4641.27 | 60948.16 | 66.6286
26 | 2001-02-21 | 29 | 143.82 | 53883 | 65871 | 2164.1396 | 1858.0345 | 2147.9087 | 2143.4319 | 2120.88 | 1896.69 | 4017.57 | 60475.3 | 65.871
27 | 2001-03-22 | 29 | 141.672 | 53929 | 65319.1667 | 2146.0096 | 1859.6207 | 2149.7377 | 2145.1745 | 2101.63 | 1898.27 | 3999.9 | 59920.88 | 65.3192
28 | 2001-04-20 | 29 | 138.096 | 49785 | 64624.9167 | 2123.2005 | 1716.7241 | 2146.1486 | 2141.755 | 1972.02 | 1752.4 | 3724.42 | 59261.9 | 64.6249
29 | 2001-05-21 | 31 | 243.95 | 60865 | 63881.75 | 2098.7844 | 1963.3871 | 2139.4004 | 2140.7009 | 2654.56 | 2142.45 | 4797.01 | 58817.25 | 63.8817
30 | 2001-06-20 | 30 | 262 | 61974 | 63018.5 | 2070.423 | 2065.8 | 2130.34 | 2125.5195 | 1491.99 | 3978.73 | 5470.72 | 58531.54 | 61.455
31 | 2001-07-20 | 30 | 263.23 | 75726 | 62644.25 | 2058.1273 | 2524.2 | 2121.5441 | 2116.8501 | 1606.06 | 4861.61 | 6467.67 | 58660.93 | 60.6184
32 | 2001-08-20 | 31 | 277.56 | 88602 | 62950.3333 | 2068.1834 | 2858.129 | 2112.7578 | 2116.3039 | 1758.83 | 5688.21 | 7447.04 | 59367.33 | 61.103
33 | 2001-09-18 | 29 | 251.52 | 63856 | 62961.7 | 2068.5569 | 2201.931 | 2134.2834 | 2136.2837 | 1470.45
34 | 2001-10-18 | 30 | 213.408 | 55043 | 62735.2 | 2061.1154 | 1834.7667 | 2136.529 | 2130.4984 | 1247.65
35 | 2001-11-16 | 29 | 202.38 | 55833 | 61949.6 | 2035.3051 | 1925.2759 | 2133.9435 | 2119.1548 | 1233.92
36 | 2001-12-19 | 33 | 152.508 | 61565 | 62717.8 | 2060.5437 | 1865.6061 | 2126.4065 | 2117.0506 | 1105.03
37 | 2002-01-23 | 35 | 146.904 | 65495 | 63874.4 | 2098.5429 | 1871.2857 | 2116.5574 | 2124.4338 | 1118.46
38 | 2002-02-21 | 29 | 150.156 | 56956 | 64591.5 | 2122.1027 | 1964 | 2114.7393 | 2122.7015 | 1061.69
39 | 2002-03-22 | 29 | 146.016 | 55188 | 64023.8 | 2103.4513 | 1903.0345 | 2095.509 | 2100.9057 | 1028.82
40 | 2002-04-22 | 31 | 226.284 | 57401 | 63566.5 | 2088.4271 | 1851.6452 | 2076.929 | 2078.6067 | 1336.08
41 | 2002-05-21 | 29 | 204.072 | 51836 | 61177.5 | 2009.9384 | 1787.4483 | 2036.6357 | 2036.2233 | 1210.74
42 | 2002-06-20 | 30 | 257.052 | 66134 | 58930.7 | 1936.1216 | 2204.4667 | 2003.7212 | 2008.1553 | 3109.97
43 | 2002-07-22 | 32 | 267.876 | 89918 | 61747.7273 | 2028.6728 | 2809.9375 | 2013.1629 | 2018.0818 | 3913.74
44 | 2002-08-20 | 29 | 261.54 | 84412 | 63636.4167 | 2090.7242 | 2910.7586 | 2059.9843 | 2062.6918 | 3714.3
45 | 2002-09-19 | 30 | 264.46 | 74278 | 64504.9167 | 2119.258 | 2475.9333 | 2091.2853 | 2096.2121 | 3398.1
46 | 2002-10-18 | 29 | 242.15 | 54482 | 64458.1667 | 2117.7221 | 1878.6897 | 2097.7436 | 2091.9918 | 2682.71
47 | 2002-11-18 | 31 | 137.64 | 54035 | 64308.3333 | 2112.7995 | 1743.0645 | 2094.2609 | 2077.5748 | 2303.64
48 | 2002-12-19 | 31 | 144.82 | 55233 | 63780.6667 | 2095.4634 | 1781.7097 | 2090.7916 | 2079.5908 | 2367.28
49 | 2003-01-23 | 35 | 142.18 | 58013 | 63157.1667 | 2074.9788 | 1657.5143 | 2081.6049 | 2085.6898 | 2390.25
50 | 2003-02-21 | 29 | 137.69 | 51828 | 62729.8333 | 2060.9391 | 1787.1724 | 2084.8071 | 2088.7407 | 2154.86
51 | 2003-03-24 | 31 | 146.47 | 51849 | 62451.5833 | 2051.7974 | 1672.5484 | 2071.5872 | 2075.2765 | 2185.09
52 | 2003-04-22 | 29 | 200.66 | 47650 | 61639 | 2025.1006 | 1643.1034 | 2052.3737 | 2053.8854 | 2244.96
53 | 2003-05-21 | 29 | 200.71 | 47217 | 61254.0833 | 2012.4545 | 1628.1724 | 2011.6451 | 2011.3108 | 2231.79
54 | 2003-06-20 | 30 | 244.44 | 55749 | 60388.6667 | 1984.0219 | 1858.3 | 1966.1984 | 1962.249 | 2054.9
55 | 2003-07-22 | 32 | 266.69 | 78850 | 59466.3333 | 1953.7194 | 2464.0625 | 1978.1134 | 1984.6407 | 2527.53
56 | 2003-08-20 | 29 | 245.45 | 69459 | 58220.25 | 1912.7803 | 2395.1379 | 2003.5849 | 2006.1691 | 2282.87
57 | 2003-09-19 | 30 | 274.22 | 67595 | 57663.3333 | 1894.4832 | 2253.1667 | 2018.489 | 2023.7342 | 2376.36
58 | 2003-10-20 | 31 | 218.02 | 49399 | 57239.75 | 1880.5667 | 1593.5161 | 2006.1213 | 2005.5658 | 1837.45
59 | 2003-11-18 | 29 | 205.04 | 50227 | 56922.4167 | 1870.141 | 1731.9655 | 1999.7885 | 1982.765 | 1795.15
60 | 2003-12-19 | 31 | 152.5 | 51542 | 56614.8333 | 1860.0356 | 1662.6452 | 1986.0906 | 1974.6799 | 1590.35
R04 | 2004-01-23 | 35 | 149.92 | 59481 | 56737.1667 | 1864.0548 | 1699.4571 | 1976.8371 | 1981.0909 | 1708.74
R04 | 2004-02-23 | 31 | 154.21 | 57550 | 57214 | 1879.7207 | 1856.4516 | 1977.0555 | 1981.3134 | 1695.72
R04 | 2004-03-23 | 29 | 151.24 | 51297 | 57168 | 1878.2094 | 1768.8621 | 1976.2107 | 1980.5085 | 1579.36
R04 | 2004-04-21 | 29 | 194.15 | 51174 | 57461.6667 | 1887.8576 | 1764.6207 | 1956.2177 | 1958.1676 | 1762.15
R04 | 2004-05-20 | 29 | 231.26 | 56033 | 58196.3333 | 1911.9945 | 1932.1724 | 1916.3193 | 1907.5647 | 2001.07
R04 | 2004-06-21 | 32 | 256.06 | 69912 | 59376.5833 | 1950.7707 | 2184.75 | 1883.3189 | 1885.9108 | 2398.59
R04 | 2004-07-21 | 30 | 247.52 | 72176 | 58820.4167 | 1932.4983 | 2405.8667 | 1880.1341 | 1882.7717 | 2400.59
R04 | 2004-08-19 | 29 | 253.21 | 66738 | 58593.6667 | 1925.0486 | 2301.3103 | 1899.3441 | 1901.0745 | 2331.8
R04 | 2004-09-20 | 32 | 233.04 | 63280 | 58234.0833 | 1913.2348 | 1977.5 | 1910.0002 | 1914.8807 | 2185.36
R04 | 2004-10-19 | 29 | 202.4 | 51783 | 58432.75 | 1919.7618 | 1785.6207 | 1910.178 | 1909.7286 | 1855.71
R04 | 2004-11-17 | 29 | 187.43 | 50076 | 58420.1667 | 1919.3484 | 1726.7586 | 1913.3255 | 1897.8757 | 1761.78
R04 | 2004-12-20 | 33 | 143.92 | 51514 | 58417.8333 | 1919.2717 | 1561.0303 | 1903.0463 | 1897.4068 | 1598.67
R04 | 2005-01-24 | 35 | 146.58 | 60232 | 58480.4167 | 1921.3279 | 1720.9143 | 1905.2448 | 1909.9257 | 1728.84
R04 | 2005-02-23 | 30 | 138.82 | 51286 | 57958.4167 | 1904.178 | 1709.5333 | 1908.2643 | 1915.3556 | 1472.4
R04 | 2005-03-23 | 28 | 123.86 | 43453 | 57304.75 | 1882.7023 | 1551.8929 | 1904.797 | 1909.7346 | 1283.24
R04 | 2005-04-21 | 29 | 180.42 | 46024 | 56875.5833 | 1868.6023 | 1587.0345 | 1892.4668 | 1895.2115 | 1566.64
R04 | 2005-05-20 | 29 | 194.94 | 46555 | 56085.75 | 1842.653 | 1605.3448 | 1853.4342 | 1846.983 | 1637.42
R04 | 2005-06-21 | 32 | 244.12 | 63764 | 55573.4167 | 1825.8207 | 1992.625 | 1835.1381 | 1838.4783 | 4940.98
R04 | 2005-07-21 | 30 | 256.2 | 79696 | 56200.0833 | 1846.4093 | 2656.5333 | 1853.473 | 1856.5496 | 5935.05
R04 | 2005-08-19 | 29 | 271.06 | 81502 | 57430.4167 | 1886.8309 | 2810.4138 | 1908.7865 | 1904.4913 | 6106.17
R04 | 2005-09-20 | 32 | 244.18 | 74958 | 58403.5833 | 1918.8036 | 2342.4375 | 1936.5352 | 1941.4239 | 5602.76
R04 | 2005-10-19 | 29 | 239.14 | 55349 | 58700.75 | 1928.5667 | 1908.5862 | 1947.7144 | 1947.1092 | 4223.43
R04 | 2005-11-17 | 29 | 136.97 | 45607 | 58328.3333 | 1916.3313 | 1572.6552 | 1941.9506 | 1926.3901 | 3239.22
R04 | 2005-12-21 | 34 | 141.65 | 54425 | 58570.9167 | 1924.3012 | 1600.7353 | 1930.3272 | 1921.7234 | 3750.3

## KWH all
2003-05-21 | 47217
2003-06-20 | 55749
2003-07-22 | 78850
2003-08-20 | 69459
2003-09-19 | 67595
2003-10-20 | 49399
2003-11-18 | 50227
2003-12-19 | 51542
2004-01-23 | 59481
2004-02-23 | 57550
2004-03-23 | 51297
2004-04-21 | 51174
2004-05-20 | 56033
2004-06-21 | 69912
2004-07-21 | 72177
2004-08-19 | 66739
2004-09-20 | 63280
2004-10-19 | 51784
2004-11-17 | 50076
2004-12-19 | 51514
2005-01-23 | 60232
2005-02-23 | 51287
2005-03-23 | 43452
2005-04-21 | 46024
2005-05-19 | 46555
2005-06-21 | 63764
2005-07-21 | 79696
2005-08-19 | 81502
2005-09-20 | 74958
2005-10-19 | 55349
2005-11-17 | 45607
2005-12-21 | 54424
2006-01-23 | 55296
2006-02-21 | 53447
2006-03-22 | 50743
2006-04-21 | 51324
2006-05-19 | 49248
2006-06-21 | 67979
2006-07-20 | 66963
2006-08-18 | 71277
2006-09-19 | 68849
2006-10-18 | 51791
2006-11-17 | 50824
2006-12-19 | 49713
2007-01-23 | 55091
2007-02-21 | 49295
2007-03-23 | 48753
2007-04-23 | 46060
2007-05-21 | 49491
2007-06-20 | 63708
2007-07-23 | 71720
2007-08-20 | 72256
2007-09-19 | 67613
2007-10-18 | 60331
2007-11-16 | 49344
2007-12-19 | 59490
2008-01-23 | 59523
2008-02-21 | 51823
2008-03-22 | 51065
2008-04-22 | 48256
2008-05-20 | 50141
2008-06-19 | 57538
2008-07-22 | 71107
2008-08-19 | 68920
2008-09-18 | 59901
2008-10-17 | 53186
2008-11-15 | 49716
2008-12-18 | 58397
2009-01-26 | 57256
2009-02-23 | 47187
2009-03-24 | 47722
2009-04-22 | 48564
2009-05-20 | 48159
2009-06-22 | 56550
2009-07-23 | 65046
2009-08-21 | 70945
2009-09-22 | 61351
2009-10-20 | 47829
2009-11-19 | 50361
2009-12-22 | 56280
2010-01-25 | 55252
2010-02-23 | 52108
2010-03-24 | 46299
2010-04-22 | 48435
2010-05-21 | 49318
2010-06-21 | 66599
2010-07-22 | 84105
2010-08-20 | 75829
2010-09-21 | 65125
2010-10-20 | 53519

## MidAmerElec
| Total KWH | Month | Total KWH
2010-10-20 | 53519 | 2004-06-21 | 69912 | Must use Firefox to login to MidAmerican
2010-09-21 | 65125 | 2004-07-21 | 72177
2010-08-20 | 75829 | 2004-08-19 | 66739
2010-07-22 | 84105 | 2004-09-20 | 63280 | Costs
2010-06-21 | 66599 | 2004-10-19 | 51784 | Energy | 3297.57 | 2870.99 | 2829 | 2673.38 | 2777.81 | 3417.18 | 4387.3
2010-05-21 | 49318 | 2004-11-17 | 50076 | Rate | 0.0554 | 0.0554 | 0.0554 | 0.0554 | 0.0554 | 0.05939 | 0.0617
2010-04-22 | 48435 | 2004-12-19 | 51514 | Losses | 259.52 | 225.95 | 222.64 | 210.4 | 218.61 | 268.93 | 345.28
2010-03-24 | 46299 | 2005-01-23 | 60232 | Rate | 0.00436 | 0.00436 | 0.00436 | 0.00436 | 0.00436 | 0.00467 | 0.00486
2010-02-23 | 52108 | 2005-02-23 | 51287 | Capacity | 245.83 | 214.03 | 210.9 | 199.3 | 207.08 | 0 | 0
2010-01-25 | 55252 | 2005-03-23 | 43452 | Rate | 0.00413 | 0.00413 | 0.00413 | 0.00413 | 0.00413 | 0 | 0
2009-12-22 | 56280 | 2005-04-21 | 46024 | Transmission | 247.02 | 215.07 | 211.92 | 187.72 | 209.59 | 240.51 | 342.02
2009-11-19 | 50361 | 2005-05-19 | 46555 | Rate | 0.00415 | 0.00415 | 0.00415 | 0.00389 | 0.00418 | 0.00418 | 0.00481
2009-10-20 | 47829 | 2005-06-21 | 63764 | Ancillary | 111.31 | 96.91 | 95.49 | 90.24 | 93.76 | 107.59 | 114.48
2009-09-22 | 61351 | 2005-07-21 | 79696 | Rate | 0.00187 | 0.00187 | 0.00187 | 0.00187 | 0.00187 | 0.00187 | 0.00161
2009-08-21 | 70945 | 2005-08-19 | 81502 | MidAmerican | 4161.25 | 3622.95 | 3569.95 | 3361.04 | 3506.85 | 5077.34 | 6232.21
2009-07-23 | 65046 | 2005-09-20 | 74958 | Unit Rate | 0.06991 | 0.06991 | 0.06991 | 0.06965 | 0.06994 | 0.08824 | 0.08765
2009-06-22 | 56550 | 2005-10-19 | 55349 | Delivery | 946.09 | 965.4 | 897.08 | 857.92 | 1182.73 | 1424.38 | 1493.06
2009-05-20 | 48159 | 2005-11-17 | 45607 | Unit Rate | 0.01589 | 0.01863 | 0.01757 | 0.01778 | 0.02359 | 0.02476 | 0.021
2009-04-22 | 48564 | 2005-12-21 | 54424 | Total | 5107.34 | 4588.35 | 4467.03 | 4218.96 | 4689.58 | 6501.72 | 7725.27
2009-03-24 | 47722 | 2006-01-23 | 55296 | Unit Rate | 0.0858 | 0.08854 | 0.08748 | 0.08743 | 0.09353 | 0.113 | 0.10864
2009-02-23 | 47187 | 2006-02-21 | 53447
2009-01-26 | 57256 | 2006-03-22 | 50743
2008-12-18 | 58397 | 2006-04-21 | 51324
2008-11-15 | 49716 | 2006-05-19 | 49248
2008-10-17 | 53186 | 2006-06-21 | 67979
2008-09-18 | 59901 | 2006-07-20 | 66963
2008-08-19 | 68920 | 2006-08-18 | 71277
2008-07-22 | 71107 | 2006-09-19 | 68849
2008-06-19 | 57538 | 2006-10-18 | 51791
2008-05-20 | 50141 | 2006-11-17 | 50824
2008-04-22 | 48256 | 2006-12-19 | 49713
2008-03-22 | 51065 | 2007-01-23 | 55091
2008-02-21 | 51823 | 2007-02-21 | 49295
2008-01-23 | 59523 | 2007-03-23 | 48753
2007-12-19 | 59490 | 2007-04-23 | 46060
2007-11-16 | 49344 | 2007-05-21 | 49491
2007-10-18 | 60331 | 2007-06-20 | 63708
2007-09-19 | 67613 | 2007-07-23 | 71720
2007-08-20 | 72256 | 2007-08-20 | 72256
2007-07-23 | 71720 | 2007-09-19 | 67613
2007-06-20 | 63708 | 2007-10-18 | 60331
2007-05-21 | 49491 | 2007-11-16 | 49344
2007-04-23 | 46060 | 2007-12-19 | 59490
2007-03-23 | 48753 | 2008-01-23 | 59523
2007-02-21 | 49295 | 2008-02-21 | 51823
2007-01-23 | 55091 | 2008-03-22 | 51065
2006-12-19 | 49713 | 2008-04-22 | 48256
2006-11-17 | 50824 | 2008-05-20 | 50141
2006-10-18 | 51791 | 2008-06-19 | 57538
2006-09-19 | 68849 | 2008-07-22 | 71107
2006-08-18 | 71277 | 2008-08-19 | 68920
2006-07-20 | 66963 | 2008-09-18 | 59901
2006-06-21 | 67979 | 2008-10-17 | 53186
2006-05-19 | 49248 | 2008-11-15 | 49716
2006-04-21 | 51324 | 2008-12-18 | 58397
2006-03-22 | 50743 | 2009-01-26 | 57256
2006-02-21 | 53447 | 2009-02-23 | 47187
2006-01-23 | 55296 | 2009-03-24 | 47722
2005-12-21 | 54424 | 2009-04-22 | 48564
2005-11-17 | 45607 | 2009-05-20 | 48159
2005-10-19 | 55349 | 2009-06-22 | 56550
2005-09-20 | 74958 | 2009-07-23 | 65046
2005-08-19 | 81502 | 2009-08-21 | 70945
2005-07-21 | 79696 | 2009-09-22 | 61351
2005-06-21 | 63764 | 2009-10-20 | 47829
2005-05-19 | 46555 | 2009-11-19 | 50361
2005-04-21 | 46024 | 2009-12-22 | 56280
2005-03-23 | 43452 | 2010-01-25 | 55252
2005-02-23 | 51287 | 2010-02-23 | 52108
2005-01-23 | 60232 | 2010-03-24 | 46299
2004-12-19 | 51514 | 2010-04-22 | 48435
2004-11-17 | 50076 | 2010-05-21 | 49318
2004-10-19 | 51784 | 2010-06-21 | 66599
2004-09-20 | 63280 | 2010-07-22 | 84105
2004-08-19 | 66739 | 2010-08-20 | 75829
2004-07-21 | 72177 | 2010-09-21 | 65125
2004-06-21 | 69912 | 2010-10-20 | 53519

## H20 Chem
Normal Range Limits
| High | Low | 2005-08-12
Sample
Field Test
Cooling Tower
CaH |  |  | 500
P Alk. |  |  | 82
M Alk |  |  | 290
OH Alk |  |  | 0
Chloides |  |  | 50
Phosphates
Sulfite
Conductance TDS MMHOS |  |  | 860
pH |  |  | 7.5
Nitrite
Iron
Moblidimum
Chilled Water
Nitrite |  |  | 400
Boiler Water
Nitrite |  |  | 400
City Water
Well Water

## Belts
Length
UNiT | Type of Drive | Manufacture | Belt Designation | Outside Length " | Shaft CL | Shive Dia | Shive Dia | Approx. | Actual
Cooling Tower | Belt |  |  |  | 52 | 7 | 19 | 185.6764
S! | Belt
S2 | Belt |  | B47 - 1A 106 | [5 empty] | 106
S3 | Belt |  | 5L440 (Grainger) or B41 | [5 empty] | 41
Unknown |  |  | Bx99 | [5 empty] | 99
Unknown |  |  | 4L - 540 | [5 empty] | 50
Unknown |  |  | 4L - 400 | [5 empty] | 40
Unknown |  |  | 5L - 370 | [5 empty] | 30
Unknown |  |  | X13 - 660 | [5 empty] | 25
Unknown |  |  | A46 / 3X - 471 | [5 empty] | 48
Unknown |  |  | A48 - 3X - 472 | [5 empty] | 48
ER1
ER2
ER3 500 W. Wood Bathrooms
Air Compressor | [7 empty] | 40
E1
E2 smaller of 2 small vent fans at south end of high roof)
E3 (larger of 2 small vent fans at south end of high roof) |  |  | 4L310 (Grainger) 6832 437ET | 31 inches
Roof HVAC - 207 office
Roof HVAC - 207 Lab
Roof HVAC - 220 office
Roof HVAC - 200 Shop

## Motors
| Date greased | BELT # | Voltage | Moter HP. | Frame # | Phase | Amps | RPM | Location | BELTCHANGE | SERVICE FACT.
S-1 | 1995-06-12 | (3X) B-34 | 480 to Ground | 15 | 254T | 3 | 19 |  | Mech Rm | 1995-06-07
S-2 | 1995-06-12 | (2X) B-47 | 480 to Ground | 20 | 256T | 3 | 25 | 1770 | Mech Rm | 8/21/95
S-3 | 1995-06-12 | (3X) B-41 | 480 to Ground | 25 | 284T | 3 | 30 | 1770 | Mech Rm | 1995-06-12
ER-1 | 1995-06-12 | (2X) A-73 | 480 to Ground | 3 | 145T | 3 | 9.2/4.6 | 1725 | Mech RM
ER-2 | 1995-06-12 | (2X) BX-99 | 480 to Ground | 7.5 | 213T | 3 | 22.8/11.4 | 1745 | Mech Rm
ER-3 | 1995-06-12 | (2X) BX-99 | 480 to Ground | 7.5 | 213T | 3 | 22.8/11.4 | 1745 | Mech Rm
HP-1 | 1995-06-12 | None | 480 to Ground | 5 | 184T | 3 | 13.4/6.7 | 1715 | Mech Rm
HP-2 | 1995-06-12 | None | 480 to Ground | 15 | 254T | 3 | 42.638.419.2 | 1745 | Mech Rm
HP-3 | 1995-06-12 | None | 480 to Ground | 3 | 182T | 3 | 9.5/9.5/4.5 | 1740 | Mech Rm
HP-3A | 1995-06-12 | None | 480 to Ground | 3 | 182T | 3 | 9.5/9.0/4.5 | 1740 | Mech Rm
HP-4 | 1995-06-12 | None | 480 to Ground | 5 | 184T | 3 | 13.4/6.7 | 1715 | Mech Rm
HP-5 |  | None | 480 to Ground | 1 |  | 3 | 3.6/1.8 | 1725 | Mech Rm
HP-7 |  | None | 480 to Ground | 2 | 56H | 3 | 6.6/6.6/3.3 | 1725 | Mech Rm
HP-8 |  | None | 480 to Ground | 2 | 56Y | 3 | 6.2/3.1 | 1725 | Mech Rm
HP-9 |  | None | 480 to Ground | 2 | 56Y | 3 | 6.2/3.1 | 1725 | Mech Rm
E-1Hood ex |  | (3) B-65 | 480 to Ground | 10 | L215T | 3 | 26/13 | 1740 | 500 Roof |  | 1.15
Cooling TOWER |  | (2X) B-144 | 480 to Ground | [5 empty] | 500 Roof
Mens E3 Fan |  | (1) 6832 | [6 empty] | 500 Roof
Bathrm EX |  | (1) 5L330 | 230/460 | 3/4 | G56 | 3 | 2.4/1.2 | 1725 | 500 Roof |  | 4
Acid Stack |  | (1) 5L330
Warehouse Hood
Warehouse Roof Ventilator

## Completed Summer 01
Priority | JOB | Finished to/date | Assigned by/date | Inspected By/Date | Procedure Done | PDSA
Done | Replace bad light Bulbs in all buildings
Done | Dry Marker Boards in conference rooms
Done | Flip Charts in Conference Rooms
PDS | Seal north stairwell at roof
PDS | Fix Express AC condensate leak
Intern feedback form
Pictures of new employees on Intranet

## Summer Processes
Priority | JOB | 2004 | 2003 | 2002 | 2001 | Pre 2001 | PDSA
A1 | Walls, doors etc. fix, plaster and paint |  |  |  | Jodi & Mike A lot
A | Inspect Locks and Weatherstrip
A | Inspect Cooling tower Orfice distribuator, fill, belts and sump.
A | Grease all Fan and Pump Bearings |  | Some | Some
A | Clean out Area wells, especially Air Intake. |  | YES | YES
A | Fix drain in air intake or install peristaltic pump. Get a price from a contractor to cut concrete to get at pipe and fix. | Clean out gravel then Just Check it. | YES it is done!
A | E1 fan inlet expansion joint Replacement if needed.
A | Drain generator, replace generator engine rubber, flush radiator and refill antifreeze. | Should be OK until 2005 |  |  | Vince Ferro & Jeff Capek
A | Inventory bad ceiling tiles and check MR for replacements. Order replacements if needed. | Check and do some |  | Will Prebel did it
A | Inspect warehouse floors
A | Do & Put Maintenance Check List Online
B | Cooling Tower fan belts look loose. Replacement if needed. |  | Jaun did it
B | Install generator CO monitor on EP
B | Run engine with hand held CO monitor to find leak.
B | Check all fan vibration and record
B | Inspect and run Generator and Transfer Switch
C | Inspect and fix Bathroom Soap Dispensers
C | Wallpaper boardroom and elevator areas
C | Clean wallpaper in bathrooms
Do light Bulbs in all buildings
PDS | Fix Express AC condensate leak
Lab hood bafffle plates
Add 300 pounds to fan inertia pad to see how much the natural frequency changes.
Sketch a plan for board room closet
Set up manual for cleaning
Change generator oil
Intern feedback each month
Mentor feedback each month
Landscape plan
Door kickplates
Ceiling tiles replace and repair
Carpet replace
Room inspections
Volleyball court repair
Drywall repair
Paint Structures on Roofs
207 Space heater replacement
Clean and detail old trucks
Ask each team for their list of most annoying stuff
Clean truck dock drains and make cover screen
Intern summer shirts

## Summer 01 Proj
Priority | JOB | Finished to/date | Assigned by/date | Inspected By/Date | Procedure Done | PDSA
A | Operate Warehouse fans on CO level
A1 | Fix, paint and kickplate North Dooor
A | Lunch room door - Lock Cover Plate for Weatherstrip
A | Clean out Area wells, especially Air Intake.
A | Fix drain in air intake or install peristaltic pump. Get a price from a contractor to cut concrete to get at pipe and fix.
A | E1 fan inlet expansion joint Replacement if needed.
A | Drain generator, replace generator engine rubber, flush radiator and refill antifreeze.
A | Inventory bad ceiling tiles and check MR for replacements. Order replacements if needed.
A | Epoxy 207 warehouse floor - match existing
A | Do & Put Maintenance Check List Online
B | Cooling Tower fan belts look loose. Replacement if needed.
B | Install generator CO monitor on EP
B | Run engine with hand held CO monitor to find leak.
B | Grease all fan and pump bearings (fans ER1,2,3 done)
B | E1 fan inlet plenum has a come-a-long ?? remove
B | FIX or replace Generator Transfer Switch
B | Redo 207 Bathroom vent fans
C | Replace temporary lighting wire in warehouse
C | Rewire elect room exaust fan on EP
C | Check out LP-B 30 AMP breaker and update list
C | Paint 212 floor and West stairs
C | Wire shipping computer and light on UPS
C | Rewire 212 router on UPS
C | Fix Bathroom Soap Dispensers
C | Paint Structures on Roofs
C | Wallpaper boardroom and elevator areas
C | Clean wallpaper in bathrooms
Done | Do light Bulbs in all buildings
Done | Dry Marker Boards in conference rooms
Done | Flip Charts in Conference Rooms
PDS | Seal north stairwell at roof
PDS | Fix Express AC condensate leak
Lab hood bafffle plates
Add 300 pounds to fan inertia pad to see how much the natural frequency changes.
Sketch a plan for board room closet
Set up manual for cleaning
Change oil on generator
Intern feedback each month
Mentor feedback each month
Landscape plan
Door kickplates
Ceiling tiles replace and repair
Carpet replace
Room inspections
Volleyball court repair
Drywall repair
Paint Structures on Roofs
207 Space heater stack fix
Clean and detail old trucks
Ask each team for their list of most annoying stuff
Clean truck dock drains and make cover screen
Intern summer shirts

## HVAC LOC VARS
Local Variables for HVAC Program
LOC | CPU | LINE SET @ | Purpose
1 | 1 | 3790 | Call for heat from??
$LOC1 | 1 | 3001
2 | 1 | 3790
3
4
5
6
$LOC7 | 1 | 3401
$LOC8 |  | 3410 | If HP3 ON Starts HP8
9
10
$LOC11 | 1 | 4000-4020 | Hold Vapor Pressure intermediate var
12
$LOC13 | 1 |  | Sets S2 override time into seconds
$LOC14 | 1 | 2740 ON 2070 OFF | S2 override ON/OFF Latch
$LOC15 | 1
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38 | 1 | 2075 | same as $LOC14
39 | 1 | 3401-3402