## Procedures
Welcome to the CleanAir Project Planning System for Long Lead Time Project
This system is intended for the more complex and thus longer projects.
Before | using the templates make a Project Plan outline on paper using the decimal numbering system. these numbers will then be the Task #'s.
The blank template terms are defined as:
Project #: This is the CleanAir project number for financial accountability.
Objective: This is the objective for THE TASK not the Project. Should include Quanity, Quality and Time (QQT).
Project Manager: This is the Buck Stops Here Person of this task. This is the person that needs to know of any problems which may compromise project success.
Resource: This is the person, company or team accountabile for the task.
Benefit(NPV)/Cost: This is the total value of the TASK. Use NPV of all the benefits divided by cost of time and material including all overheads
Start Constraint: The thing or other TASK that is expected to hold up start on this TASK. Try to break it!
Start Time: Date and time TASK will or did start.
Finish: Date and time TASK will or did finish.
Supplier: Internal or external. Show major on front and list others on back.
Cycle Time: Da!
Customer: Internal or external. Show major on front and list others on back.
Value: This is a ratio of bottom line benefit to cost. Show value of TASK for both customer and CleanAir.
Metric: Main measurements of success of objective, QQT.
Keys From Lessons Learned: Use lessons learned database. Don't forget to add your lessons learned to the database.

## Blank Template
PROJECT PLANNING SYSTEM
CAE LOGO | Project#:
Objective:
Project Manager: | TASKS:
Task #:
Resource:
Benefits(NPV)/Cost:
Start Constraint: | Supplier: | Value:
Start Time: | Cycle Time: | Metric:
Finish Time: | Customer: | Key From Lessons Learned:
© Clean Air Engineering, Inc.
PROJECT PLANNING SYSTEM
CAE LOGO | Project#:
Objective:
Project Manager: | TASK:
Task #:
Resource:
Benefits(NPV)/Cost:
Start Constraint: | Supplier: | Value:
Start Time: | Cycle Time: | Metric:
Finish Time: | Customer: | Key From Lessons Learned:
© Clean Air Engineering, Inc.

## Example
PROJECT PLANNING SYSTEM
CAE LOGO | Project#: 9999 USX | USX Sinter CEM Intergrated System
Objective: QA/QC Plan that is acceptable to IDEM, USX and CAE by Nov 1
Project Manager: | TASK: Prepare a QA/QC plan that is a working document.
Don Hennning | Survey other best in class QA/QC plans and strive for a world class plan.
Task #: | Gather input from those who have had to live with similiar plans.
3.5.2 | Do the plan in Microsoft Word.
Resource: | Issue Outline by Sept 30, Draft by Oct 10. Submit final Plan to IDEM and USX by Oct 20.
Scott Evans | Incorporate comment and final by Oct 30.
Benefits(NPV)/Cost: | Training in use of the plan or and audit of process using the plan is not part of this task. Potential value.
12300
Start Constraint: | Supplier: | Value: Customer value is unhindered production ~ $50,000/20,000 = 2.5
Sales Release & Job# | John Chapman | System reliability and up time & continually reducing cost. CAE =20/12.3=1.6 |  | 1.626
Start Time: | Cycle Time: | Metric:
1998-09-16 | 6 Weeks | Words and steps. Target is 10 pages or less. Success % = Actual pages/10.
Finish Time: | Customer: | Key From Lessons Learned:
1998-10-31 | Don Hennning | Keep it simple.
© Clean Air Engineering, Inc.
PROJECT PLANNING SYSTEM
CAE LOG+A46O | Project#:
Objective:
Project Manager: | TASK:
Task #:
Resource:
Benefits(NPV)/Cost:
Start Constraint: | Supplier: | Value:
Sales Release & Job#
Start Time: | Cycle Time: | Metric:
1998-09-16
Finish Time: | Customer: | Key From Lessons Learned:
© Clean Air Engineering, Inc.
Rate
Mailing |  |  | 100
Copier |  |  | 200
Hours of Scott | 40 | 200 | 8000
Hours of Edna | 10 | 75 | 750
Hours of Kirk | 20 | 100 | 2000
Hours of Patricia | 10 | 75 | 750
Hours of Marion | 10 | 50 | 500
Total |  |  | 12300